## 1. Agenda
Agenda
Agenda_No | Agenda_Item
1 | Minutes of Meeting : Last Meeting
2 | IT Operations & Service Management Dashboard – Apr to July
3 | Autonomous Service Desk Operations
4 | Automation : Progress Summary
5 | Vulnerability Remediation : Progress Summary
6 | Value Co creation: IT Infra
7 | Value Co creation: IT Security
8 | Pending Ticket Analysis
9 | Projects & Demand Support

## 2. Previous MoM
Action Items
Action_No | Action | Type | Type_Description | Owner | Original_Due_Date | Revised_Due_Date | Status | Remarks
1 | New Contract commenced w.e.f 1st Apr’2026. Last two months MS support highlights and efforts consumed in value co-creation, presented by TechM Delivery Head (Sudesh) | I | Information | TechM | 2026-06-29 |  | Closed
2 | TechM to present the Automation and AI Progress w.r.t 32 USE CASE presented during RFP defence proposal, in next review meeting. | A | Action | TechM | 2026-07-27 |  | On going | Included in deck
3 | Patching through Qualys TOOL has been tested successfully. TechM to present the Qualys Patching status in next review meeting. | A | Action | TechM | 2026-07-27 |  | On going | Project Progress included in deck.
4 | TechM to present the Open Ticket Summary and Ticket Resolution Trend through Automation. Purpose is to review the progress | A | Action | TechM | 2026-07-27 |  | Closed | Included in deck
5 | On Hold Tickets will be audited for proper justification and update compliance on ITSM TOOL | A | Action | TechM | 2026-07-27 |  | Closed | Pending Tickets Analysis updated in deck
6 | Explore possibility to create single pane of glass using Azure Foundry capabilities, instead of multiple Power BI Dash-boards currently used for Operational purpose | A | Action | TechM | 2026-07-27 | 2026-09-30 | Open | 03 Foundry SMEs on-boarded, USE CASE identification and approval in progress

## 3. IT Ops
| Availability |  |  |  | CSAT/DSAT |  |  |  | Change Management |  |  |  |  | Major Incidents Volume |  |  | SLA / KPI Reporting | [6 empty] | Key Observations
| Month | Availability | Target |  |  | CSAT Score | Target |  |  | Success | Failed | Change Success (%) |  |  | Major Incidents Count |  |  | Total KPIs | Applicable | Met | Not Met | Can't be Measured |  | S/N | Updates
Insert Last 6 months of data here | 2026-04-26 | 99.83% | 99% | Insert Last 6 months of data here | 2026-04-26 | 4.5 | 4.5 | Insert Last 6 months of data here | 2026-04-26 | 96 | 4 | 96% | Insert Last 6 months of data here | 2026-04-26 | 2 | Insert Last 6 months of data here | 2026-04-26 | 56 | 32 | 28 | 1 | 3 | Insert Max 6 key points here | 1 | Steady INFRA Availability with July at 99.81%.
| 2026-05-26 | 99.74% | 99% |  | 2026-05-26 | 4.6 | 4.5 |  | 2026-05-26 | 94 | 6 | 94% |  | 2026-05-26 | 0 |  | 2026-05-26 | 56 | 32 | 29 | 0 | 3 |  | 2 | CSAT maintained at 4.54.
| 2026-06-26 | 99.81% | 100% |  | 2026-06-26 | 4.6 | 4.5 |  | 2026-06-26 | 96 | 4 | 96% |  | 2026-06-26 | 0 |  | 2026-06-26 | 56 | 52 | 46 | 0 | 6 |  | 3 | Change success at 99% in July.
| 2026-07-26 | 99.81% | 100% |  | 2026-07-26 | 4.54 | 4.5 |  | 2026-07-26 | 97 | 3 | 97% |  | 2026-07-26 | 1 |  | 2026-07-26 | 56 | 29 | 29 | 1 | 3 |  | 4 | No Major Incidents reported in May & June
| 2026-08-26 | 99.82% | 100% |  | 2026-08-26 | 4.55 | 4.5 |  | 2026-08-26 | 96 | 4 | 96% |  | 2026-08-26 | 0 |  | 2026-08-26 | 56 | 36 | 28 | 0 | 3 |  | 5
| 2026-09-26 | 99.83% | 100% |  | 2026-09-26 | 4.56 | 4.5 |  | 2026-09-26 | 98 | 2 | 98% |  | 2026-09-26 | 1 |  | 2026-09-26 | 56 | 40 | 29 | 0 | 6 |  | 6
[9 empty] | Last 6 months' average |  |  | 96.17%

## 4. Tickets
[23 empty] | Ageing by Ticket Type / Assignment Group / Bucket |  |  |  | Hold Reasons
| Monthly Closure Trend |  |  |  | Team Ticket Volumetrics |  |  |  | Top 5 INC Categories |  |  |  | Top 5 SR Categories |  |  | Service Desk Support Volumetrics for the reporting month | [6 empty] | Ticket_Type | Assignment_Group | Age_Bucket | Count | Ticket_Type | Hold_Reason | Count | Share_Pct | Definition
|  | Incidents | SCTASK |  | Group | INC Count | SR Count |  | S/N | INC Category | Count |  | S/N | SR Category | Count | EndPoint Devices | Users | Tickets | Calls | Emails | Notifications | Total | Incident | DH - IT Networks | ≤ 2 | 9 | Incident | User dependency | 5 | 50 | Tickets ON HOLD by USER request for observation.
Insert Last 6 months of data here | 2026-04-26 | 1488 | 6519 | Insert Last 6 months of data here | EUS | 637 | 1439 | Insert Last 6 months of data here | 1 | Monitoring Alert | 2577 | Insert Last 6 months of data here | 1 | Leaver Deactivation (FTE Account disable) | 3717 | 10800+ | 18300+ | 3703 | 1129 | 3516 | 54 | 8402 | Incident | DH - IT Networks | 2026-03-05 | 2 | Incident | Vendor dependency | 3 | 30 | Response awaited from Principal OEM, support Ticket raised.
| 2026-05-26 | 1325 | 4340 |  | Infra | 4283 | 5086 |  | 2 | SOC | 690 |  | 2 | Consultant Outsource Account (extend disable or create FTC) | 2249 | [7 empty] | Incident | DH - IT Networks | 2026-05-10 | 2 | Incident | Late assignment | 1 | 10 | Ticket was assigned after 6 month by DHH Application team
| 2026-06-26 | 1176 | 5882 |  | Security | 69 | 1353 |  | 3 | Email | 375 |  | 3 | Distribution Group Services (add remove members or create DL) | 1778 | [7 empty] | Incident | DH - IT Networks | 2026-10-20 | 2 | Incident | Onsite dependency | 1 | 10 | Awaiting Service validation by onsite support team.
| 2026-07-26 | 1498 | 5578 |  | Service Desk | 498 | 14441 |  | 4 | Account Locked | 192 |  | 4 | Shared Folder Management | 1657 | [7 empty] | Incident | DH - IT Networks | 20-30 | 0 | SCTASK | DH Security Team | 21 | 38 | Awaiting DHIS team action.
| 2026-08-26 | 0 | 0 |  | Grand Total | 5487 | 22319 |  | 5 | Shared Folder | 173 |  | 5 | Shared Mailbox Management | 1183 | [7 empty] | Incident | DH - IT Networks | ≥ 90 | 0 | SCTASK | Change dependency | 18 | 33 | 83% are server decommissioning; remaining related to commissioning and network activity.
| 2026-09-26 | 0 | 0 | [19 empty] | Incident | DH - IT Networks | Total | 15 | SCTASK | Bulk Request | 11 | 20 | Multiple TASK /Activity in single SR, Majority related to vulnerability remediation.
| Total | 5487 | 22319 | [19 empty] | Incident | DH - IT Cloud Ops | ≤ 2 | 7 | SCTASK | User dependency | 5 | 9 | Awaiting Service validation by onsite support team.
| Grand Total | 27806 | [20 empty] | Incident | DH - IT Cloud Ops | 2026-03-05 | 0
[23 empty] | Incident | DH - IT Cloud Ops | 2026-05-10 | 1
[23 empty] | Incident | DH - IT Cloud Ops | 2026-10-20 | 0
[23 empty] | Incident | DH - IT Cloud Ops | 20-30 | 0
[23 empty] | Incident | DH - IT Cloud Ops | ≥ 90 | 0
[23 empty] | Incident | DH - IT Cloud Ops | Total | 8
[23 empty] | Incident | DH - IT Wintel & DC Ops | ≤ 2 | 3
[23 empty] | Incident | DH - IT Wintel & DC Ops | 2026-03-05 | 0
[23 empty] | Incident | DH - IT Wintel & DC Ops | 2026-05-10 | 0
[23 empty] | Incident | DH - IT Wintel & DC Ops | 2026-10-20 | 0
[23 empty] | Incident | DH - IT Wintel & DC Ops | 20-30 | 1
[23 empty] | Incident | DH - IT Wintel & DC Ops | ≥ 90 | 1
[23 empty] | Incident | DH - IT Wintel & DC Ops | Total | 5
[23 empty] | Incident | DH - IT Backup & Storage | ≤ 2 | 1
[23 empty] | Incident | DH - IT Backup & Storage | 2026-03-05 | 0
[23 empty] | Incident | DH - IT Backup & Storage | 2026-05-10 | 1
[23 empty] | Incident | DH - IT Backup & Storage | 2026-10-20 | 1
[23 empty] | Incident | DH - IT Backup & Storage | 20-30 | 0
[23 empty] | Incident | DH - IT Backup & Storage | ≥ 90 | 0
[23 empty] | Incident | DH - IT Backup & Storage | Total | 3
[23 empty] | Incident | Techhub Service Desk Team | ≤ 2 | 3
[23 empty] | Incident | Techhub Service Desk Team | 2026-03-05 | 0
[23 empty] | Incident | Techhub Service Desk Team | 2026-05-10 | 0
[23 empty] | Incident | Techhub Service Desk Team | 2026-10-20 | 0
[23 empty] | Incident | Techhub Service Desk Team | 20-30 | 0
[23 empty] | Incident | Techhub Service Desk Team | ≥ 90 | 0
[23 empty] | Incident | Techhub Service Desk Team | Total | 3
[23 empty] | Incident | DH - IT ADMM | ≤ 2 | 2
[23 empty] | Incident | DH - IT ADMM | 2026-03-05 | 0
[23 empty] | Incident | DH - IT ADMM | 2026-05-10 | 0
[23 empty] | Incident | DH - IT ADMM | 2026-10-20 | 0
[23 empty] | Incident | DH - IT ADMM | 20-30 | 0
[23 empty] | Incident | DH - IT ADMM | ≥ 90 | 0
[23 empty] | Incident | DH - IT ADMM | Total | 2
[23 empty] | Incident | DHHQ - Site Support | ≤ 2 | 1
[23 empty] | Incident | DHHQ - Site Support | 2026-03-05 | 0
[23 empty] | Incident | DHHQ - Site Support | 2026-05-10 | 0
[23 empty] | Incident | DHHQ - Site Support | 2026-10-20 | 0
[23 empty] | Incident | DHHQ - Site Support | 20-30 | 0
[23 empty] | Incident | DHHQ - Site Support | ≥ 90 | 0
[23 empty] | Incident | DHHQ - Site Support | Total | 1
[23 empty] | Incident | DHGS - Site Support | ≤ 2 | 1
[23 empty] | Incident | DHGS - Site Support | 2026-03-05 | 0
[23 empty] | Incident | DHGS - Site Support | 2026-05-10 | 0
[23 empty] | Incident | DHGS - Site Support | 2026-10-20 | 0
[23 empty] | Incident | DHGS - Site Support | 20-30 | 0
[23 empty] | Incident | DHGS - Site Support | ≥ 90 | 0
[23 empty] | Incident | DHGS - Site Support | Total | 1
[23 empty] | Incident | DH - IT Security | ≤ 2 | 0
[23 empty] | Incident | DH - IT Security | 2026-03-05 | 0
[23 empty] | Incident | DH - IT Security | 2026-05-10 | 1
[23 empty] | Incident | DH - IT Security | 2026-10-20 | 0
[23 empty] | Incident | DH - IT Security | 20-30 | 0
[23 empty] | Incident | DH - IT Security | ≥ 90 | 0
[23 empty] | Incident | DH - IT Security | Total | 1
[23 empty] | Incident | Grand Total | ≤ 2 | 27
[23 empty] | Incident | Grand Total | 2026-03-05 | 2
[23 empty] | Incident | Grand Total | 2026-05-10 | 5
[23 empty] | Incident | Grand Total | 2026-10-20 | 3
[23 empty] | Incident | Grand Total | 20-30 | 1
[23 empty] | Incident | Grand Total | ≥ 90 | 1
[23 empty] | Incident | Grand Total | Total | 39
[23 empty] | SCTASK | DH - IT Security | ≤ 2 | 22
[23 empty] | SCTASK | DH - IT Security | 2026-03-05 | 0
[23 empty] | SCTASK | DH - IT Security | 2026-05-10 | 12
[23 empty] | SCTASK | DH - IT Security | 2026-10-20 | 1
[23 empty] | SCTASK | DH - IT Security | 20-30 | 3
[23 empty] | SCTASK | DH - IT Security | ≥ 30 | 3
[23 empty] | SCTASK | DH - IT Security | ≥ 60 | 1
[23 empty] | SCTASK | DH - IT Security | ≥ 90 | 15
[23 empty] | SCTASK | DH - IT Security | Total | 57
[23 empty] | SCTASK | DH - IT Wintel & DC Ops | ≤ 2 | 11
[23 empty] | SCTASK | DH - IT Wintel & DC Ops | 2026-03-05 | 0
[23 empty] | SCTASK | DH - IT Wintel & DC Ops | 2026-05-10 | 7
[23 empty] | SCTASK | DH - IT Wintel & DC Ops | 2026-10-20 | 5
[23 empty] | SCTASK | DH - IT Wintel & DC Ops | 20-30 | 8
[23 empty] | SCTASK | DH - IT Wintel & DC Ops | ≥ 30 | 5
[23 empty] | SCTASK | DH - IT Wintel & DC Ops | ≥ 60 | 0
[23 empty] | SCTASK | DH - IT Wintel & DC Ops | ≥ 90 | 0
[23 empty] | SCTASK | DH - IT Wintel & DC Ops | Total | 36
[23 empty] | SCTASK | DH - IT Networks | ≤ 2 | 5
[23 empty] | SCTASK | DH - IT Networks | 2026-03-05 | 0
[23 empty] | SCTASK | DH - IT Networks | 2026-05-10 | 6
[23 empty] | SCTASK | DH - IT Networks | 2026-10-20 | 7
[23 empty] | SCTASK | DH - IT Networks | 20-30 | 3
[23 empty] | SCTASK | DH - IT Networks | ≥ 30 | 1
[23 empty] | SCTASK | DH - IT Networks | ≥ 60 | 0
[23 empty] | SCTASK | DH - IT Networks | ≥ 90 | 0
[23 empty] | SCTASK | DH - IT Networks | Total | 22
[23 empty] | SCTASK | DHHQ - Site Support | ≤ 2 | 12
[23 empty] | SCTASK | DHHQ - Site Support | 2026-03-05 | 0
[23 empty] | SCTASK | DHHQ - Site Support | 2026-05-10 | 3
[23 empty] | SCTASK | DHHQ - Site Support | 2026-10-20 | 0
[23 empty] | SCTASK | DHHQ - Site Support | 20-30 | 0
[23 empty] | SCTASK | DHHQ - Site Support | ≥ 30 | 0
[23 empty] | SCTASK | DHHQ - Site Support | ≥ 60 | 0
[23 empty] | SCTASK | DHHQ - Site Support | ≥ 90 | 0
[23 empty] | SCTASK | DHHQ - Site Support | Total | 15
[23 empty] | SCTASK | Techhub Service Desk Team | ≤ 2 | 7
[23 empty] | SCTASK | Techhub Service Desk Team | 2026-03-05 | 1
[23 empty] | SCTASK | Techhub Service Desk Team | 2026-05-10 | 3
[23 empty] | SCTASK | Techhub Service Desk Team | 2026-10-20 | 1
[23 empty] | SCTASK | Techhub Service Desk Team | 20-30 | 0
[23 empty] | SCTASK | Techhub Service Desk Team | ≥ 30 | 0
[23 empty] | SCTASK | Techhub Service Desk Team | ≥ 60 | 0
[23 empty] | SCTASK | Techhub Service Desk Team | ≥ 90 | 0
[23 empty] | SCTASK | Techhub Service Desk Team | Total | 12
[23 empty] | SCTASK | DH - IT ADMM | ≤ 2 | 6
[23 empty] | SCTASK | DH - IT ADMM | 2026-03-05 | 0
[23 empty] | SCTASK | DH - IT ADMM | 2026-05-10 | 4
[23 empty] | SCTASK | DH - IT ADMM | 2026-10-20 | 0
[23 empty] | SCTASK | DH - IT ADMM | 20-30 | 0
[23 empty] | SCTASK | DH - IT ADMM | ≥ 30 | 0
[23 empty] | SCTASK | DH - IT ADMM | ≥ 60 | 0
[23 empty] | SCTASK | DH - IT ADMM | ≥ 90 | 0
[23 empty] | SCTASK | DH - IT ADMM | Total | 10
[23 empty] | SCTASK | DH - IT Cloud Ops | ≤ 2 | 6
[23 empty] | SCTASK | DH - IT Cloud Ops | 2026-03-05 | 0
[23 empty] | SCTASK | DH - IT Cloud Ops | 2026-05-10 | 0
[23 empty] | SCTASK | DH - IT Cloud Ops | 2026-10-20 | 0
[23 empty] | SCTASK | DH - IT Cloud Ops | 20-30 | 0
[23 empty] | SCTASK | DH - IT Cloud Ops | ≥ 30 | 0
[23 empty] | SCTASK | DH - IT Cloud Ops | ≥ 60 | 0
[23 empty] | SCTASK | DH - IT Cloud Ops | ≥ 90 | 0
[23 empty] | SCTASK | DH - IT Cloud Ops | Total | 6
[23 empty] | SCTASK | DH - IT Backup & Storage | ≤ 2 | 3
[23 empty] | SCTASK | DH - IT Backup & Storage | 2026-03-05 | 0
[23 empty] | SCTASK | DH - IT Backup & Storage | 2026-05-10 | 1
[23 empty] | SCTASK | DH - IT Backup & Storage | 2026-10-20 | 1
[23 empty] | SCTASK | DH - IT Backup & Storage | 20-30 | 0
[23 empty] | SCTASK | DH - IT Backup & Storage | ≥ 30 | 0
[23 empty] | SCTASK | DH - IT Backup & Storage | ≥ 60 | 0
[23 empty] | SCTASK | DH - IT Backup & Storage | ≥ 90 | 0
[23 empty] | SCTASK | DH - IT Backup & Storage | Total | 5
[23 empty] | SCTASK | DH - IT SharePoint & Web Apps | ≤ 2 | 2
[23 empty] | SCTASK | DH - IT SharePoint & Web Apps | 2026-03-05 | 0
[23 empty] | SCTASK | DH - IT SharePoint & Web Apps | 2026-05-10 | 2
[23 empty] | SCTASK | DH - IT SharePoint & Web Apps | 2026-10-20 | 0
[23 empty] | SCTASK | DH - IT SharePoint & Web Apps | 20-30 | 0
[23 empty] | SCTASK | DH - IT SharePoint & Web Apps | ≥ 30 | 0
[23 empty] | SCTASK | DH - IT SharePoint & Web Apps | ≥ 60 | 0
[23 empty] | SCTASK | DH - IT SharePoint & Web Apps | ≥ 90 | 0
[23 empty] | SCTASK | DH - IT SharePoint & Web Apps | Total | 4
[23 empty] | SCTASK | DH - IT UNIX | ≤ 2 | 3
[23 empty] | SCTASK | DH - IT UNIX | 2026-03-05 | 0
[23 empty] | SCTASK | DH - IT UNIX | 2026-05-10 | 0
[23 empty] | SCTASK | DH - IT UNIX | 2026-10-20 | 0
[23 empty] | SCTASK | DH - IT UNIX | 20-30 | 0
[23 empty] | SCTASK | DH - IT UNIX | ≥ 30 | 1
[23 empty] | SCTASK | DH - IT UNIX | ≥ 60 | 0
[23 empty] | SCTASK | DH - IT UNIX | ≥ 90 | 0
[23 empty] | SCTASK | DH - IT UNIX | Total | 4
[23 empty] | SCTASK | DHGS - Site Support | ≤ 2 | 2
[23 empty] | SCTASK | DHGS - Site Support | 2026-03-05 | 0
[23 empty] | SCTASK | DHGS - Site Support | 2026-05-10 | 1
[23 empty] | SCTASK | DHGS - Site Support | 2026-10-20 | 0
[23 empty] | SCTASK | DHGS - Site Support | 20-30 | 0
[23 empty] | SCTASK | DHGS - Site Support | ≥ 30 | 0
[23 empty] | SCTASK | DHGS - Site Support | ≥ 60 | 0
[23 empty] | SCTASK | DHGS - Site Support | ≥ 90 | 0
[23 empty] | SCTASK | DHGS - Site Support | Total | 3
[23 empty] | SCTASK | Grand Total | ≤ 2 | 79
[23 empty] | SCTASK | Grand Total | 2026-03-05 | 1
[23 empty] | SCTASK | Grand Total | 2026-05-10 | 39
[23 empty] | SCTASK | Grand Total | 2026-10-20 | 15
[23 empty] | SCTASK | Grand Total | 20-30 | 14
[23 empty] | SCTASK | Grand Total | ≥ 30 | 10
[23 empty] | SCTASK | Grand Total | ≥ 60 | 1
[23 empty] | SCTASK | Grand Total | ≥ 90 | 15
[23 empty] | SCTASK | Grand Total | Total | 174

## 5. Automation
Average Interactions per Month ¦ Service Desk Volume |  | Autonomous Service Desk Maturity Index |  |  |  | Automation Use Cases ¦ Due Date: 31 Dec 2026 | [6 empty] | Automation Summary | [6 empty] | Active Directory Hygiene & Clean ups
Particulars | Count | Achieved | Target | Due Date | Status | Type | Identified | Active | Planned | Completion Target (~70%) | Status |  | Type | TechHub | Automation | Total Use Cases Deployed | Tickets Automated | Overall SOPs Automated | Use Cases Live | Licenses Released | 1311 | Mailbox Policies Applied | 289 | Stale Items Disabled | 2732
Tickets | 3613 | 12% | 30% | 2026-12-31 | Ahead of Schedule | InfraOps | 16 | 9 | 7 | 11 | Ahead of Schedule | Insert all available data here | 2026-04-26 | 6519 | 1408 | 9 | 4470 | 31 | 56 | SPE-F1 | 825 |  |  | Computers | 1189
Emails | 3084 |  |  |  |  | SecOps | 16 | 9 | 7 | 11 | Ahead of Schedule |  | 2026-05-26 | 4340 | 978 |  |  |  |  | SPE-E5 | 335 |  |  | User Accounts | 1543
Calls | 1265 |  |  |  |  | Total | 32 | 18 | 14 | 22 | Ahead of Schedule |  | 2026-06-26 | 5882 | 1028 |  |  |  |  | MS-E7 | 151
Notifications | 49 | [11 empty] | 2026-07-26 | 5578 | 1056
Total Monthly Interactions | 8011 | [11 empty] | 2026-08-26 | 0 | 0
[13 empty] | 2026-09-26 | 0 | 0
[13 empty] | 2026-10-26 | 0 | 0
[13 empty] | 2026-11-26 | 0 | 0
[13 empty] | 2026-12-26 | 0 | 0
[13 empty] | SRs processed by Automation | 4470
[13 empty] | SRs processed by TechHub | 22319
[13 empty] | Automation Achieved (approx.) | 16.69%

## 6. Vulnerability
Monthly Vulnerability Mitigation Progress Trend (for Critical+High+Medium) | [7 empty] | Total Vulnerabilities | Category | Vulnerability Type | Top Infra Contributors | Count | Top App_Dependent Contributors | Count
Vulnerability Status | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | Open Vulnerabilities (Infra + App Dependent) Total - [252K] >30 Days - [184K] (~25K exclusions,cleanup approved. Qualys is creating rules) 0-30 Days - [68K] | Windows Total - [208K] | Servers Vulnerabilities Count [Infra - 19K] [App Dependent - 18K] [Total - 37K] | Windows OS Products | 8.3K | Office | 1.7K
Vulnerabilities Fixed | 108 | 121 | 103 | 168 | 170 | [5 empty] | Chrome | 3.5K | .net framework | 1.4K
Open Vulnerabilities (>30 Days) | 253 | 175 | 127 | 116 | 96 | [5 empty] | Edge_chromium | 2.0K | .net | 179
New Vulnerabilities | 30 | 73 | 92 | 148 | 164 | [5 empty] | Firefox | 657 | SQL server | 552
[11 empty] | IE | 206 | 7-zip | 249
[10 empty] | Client Vulnerabilities Count [Infra - 97K] [App Dependent - 74K] [Total - 171K] | Windows OS Products | 57K | 7-zip | 14.7K
[11 empty] | Chrome | 27K | .net | 8.3K
[11 empty] | Edge_chromium | 4.6K | Java | 5.8K
[11 empty] | Forticlient | 5.6K | .net_framework | 7.2K
[11 empty] | Notepad | 3.1K | Office | 7.4K
Application Dependent Vulnerabilities Count [92K]
[9 empty] | Non-Windows Total - [44K] | Linux Servers Vulnerabilities Count [Infra - 5.7K] [App Dependent - 1.1K] [Total - 6.8K] | Kernel | 2.5K | python3 | 410
[11 empty] | Vim | 300 | openssl | 201
[11 empty] | libxml2 | 250 | samba | 60
[11 empty] | glibc | 230 | Java | 55
[11 empty] | glib2 | 210 | Openjdk | 31
[10 empty] | Network/Storage/Database/SharePoint/ADMM/Others [Infra - 38.3K] [App Dependent - 1.5K] [Total - 37.4K] | Openssh | 8.0K | httpserver | 165
[11 empty] | JunOS | 2.1K | openssl | 98
[11 empty] | FortiOS | 650 | tomcat | 90
[11 empty] | IOS_xe | 480 | aos | 85
[11 empty] | IOS | 310 | .net | 30
Application Dependent Vulnerabilities Count [2.6K]

## 7. Risk
| Summary | Last 30 Days Risk Closure |  |  | Risks with No Target Date |  |  |  | Requires Attention |  | Last 30 Days Risk Closure |  |  |  | Risks with No Target Date |  |  |  |  | Requires Attention | [5 empty] | Overdue Risk Summary
Total | 599 | Dependency | Count | Share_Pct | Entity | Count | Share_Pct | Data_Quality | Entity | Count |  | Month | Entity | Count |  | Risk_Number | Risk_Name | Risk_Description | Potential_Impact | Entity | Sub_Entity | Expected_Date_Of_Closure | Action_Plan | Accountability | Owner | Metric | Value
Open | 56 | Project Dependency | 2 | 50 | DHH | 11 | 45.83 | Explicit label | DHHQ | 12 |  | 2026-08-01 | DHAM | 6 |  | DHHQ-15 | Vulnerabilities for ESXI Platforms onf VMWARE and Vxrail | Esxi Platform Vulnerabilities are reported on VXRAIL and Standalone Esxi hosts | HIGH | DHHQ | ATS | 2026-04-30 | 1. EXSI Platforms to be upgraded to the versions which aren’t vulnerable. 2. Wintel is preparing the action plan with vendor CDA 3. Broadcom License consolidation dependency is there | Murtuza Sathaliya | Mathew Sheath | Overdue Risk Count as on 26 Aug | 5
Closed | 543 | Vendor Dependency | 1 | 25 | DHHQ | 9 | 37.5 | Explicit label | DHH | 9 |  | 2026-08-01 | DHE | 3 |  | DHHQ-09 | Vulnerabilities for ESXI Platforms onf VMWARE and Vxrail | Esxi Platform Vulnerabilities are reported on VXRAIL and Standalone Esxi hosts | HIGH | DHHQ | IMPZ | 2026-05-31 | 1. EXSI Platforms to be upgraded to the versions which aren’t vulnerable. 2. Wintel is preparing the action plan with vendor CDA 3. Broadcom License consolidation dependency is there | Murtuza Sathaliya | Mathew Sheath | VMWARE license dependency related | 4
New Risks | 0 | Entity Dependency | 1 | 25 | DHE | 2 | 8.33 | Explicit label; percent visually truncated but count/total gives 8.33% | DHE | 8 |  | 2026-08-01 | DHGS | 1 |  | DHHQ-11 | Vulnerabilities for ESXI Platforms onf VMWARE and Vxrail | Esxi Platform Vulnerabilities are reported on VXRAIL and Standalone Esxi hosts | HIGH | DHHQ | DPR | 2026-05-31 | 1. EXSI Platforms to be upgraded to the versions which aren’t vulnerable. 2. Wintel is preparing the action plan with vendor CDA 3. Broadcom License consolidation dependency is there | Murtuza Sathaliya | Mathew Sheath | Entity dependency related | 1
Overdue | 6 |  |  |  | DHAM | 1 | 4.17 | Explicit label | DHAM | 7 |  | 2026-08-01 | DHH | 1 |  | DHHQ-12 | Vulnerabilities for ESXI Platforms onf VMWARE and Vxrail | Esxi Platform Vulnerabilities are reported on VXRAIL and Standalone Esxi hosts | HIGH | DHHQ | GV | 2026-07-31 | 1. EXSI Platforms to be upgraded to the versions which aren’t vulnerable. 2. Wintel is preparing the action plan with vendor CDA 3. Broadcom License consolidation dependency is there | Murtuza Sathaliya | Mathew Sheath
[16 empty] | DHRE-02 | Unplanned Power and Cabling outages at NSO DataCenter | Due to ongoing multiple site refresh activities at NSO, IT is facing multiple unplanned service outages. As NSO is a Data Center, the outages are getting extended to all NSO hosted sites and critical applications | CRITICAL | DHRE | Nakheel | 2026-08-15 | Multiple MIs have occurred due to unplanned power and cabling activities at the site. Entity has confirmed that renovation works are to be completed by Feb 2026. Date revised as per extension work update | Praseetha Mohan | Vipin Aggarwal

## 8.AIOPS Roadmap
Roadmap Activities
Workstream | Activity | Start_Quarter | End_Quarter
Automation Enhancement | Existing Automation Review | Q2 2026 | Q2 2026
Automation Enhancement | SolarWinds Integration | Q2 2026 | Q2 2026
Automation Enhancement | Standardize workflows, orchestration across platform | Q3 2026 | Q1 2027
Automation Enhancement | SNOW Integration | Q3 2026 | Q1 2027
New Automation Use Cases | New Use Case Identification, Review, Feasibility and Deployment | Q2 2026 | Q2 2026
New Automation Use Cases | New Automation Use case development | Q3 2026 | Q3 2026
New Automation Use Cases | Automation based on trends, events, threshold, incident and requests | Q4 2026 | Q1 2027
Tools + AIOps | Alert Reduction on Solar Wind ITOM TOOL using AI capability | Q3 2026 | Q3 2026
Tools + AIOps | Use Case Development | Q4 2026 | Q1 2027
Gen AI L2/L2 Ops | AI Team Onboarding | Q2 2026 | Q2 2026
Gen AI L2/L2 Ops | AI Use case identification and Feasibility | Q2 2026 | Q2 2026
Gen AI L2/L2 Ops | Gen AI powered L2 operations for troubleshooting and ticket handling | Q3 2026 | Q1 2027
Gen AI L2/L2 Ops | AI Assisted Incident summarization and RCA | Q3 2026 | Q1 2027
Gen AI L2/L2 Ops | Automated Diagnostics | Q3 2026 | Q1 2027
Gen AI L2/L2 Ops | Anomaly detections | Q3 2026 | Q1 2027
Agentic AI | Evaluation, feasibility, development and deployment of one or two use cases | Q3 2026 | Q1 2027
Agentic AI | Chatbot Use case | Q3 2026 | Q1 2027
Agentic AI | Knowledge base use case | Q3 2026 | Q1 2027
Agentic AI | Incident Resolution | Q3 2026 | Q1 2027
Agentic AI | Service Request fulfillment | Q3 2026 | Q1 2027

## 10. Color Schema
Color Schema
General
Input | Purpose | Primary | Hover Darken % | Active Darken % | Lighten % | Border Lighten % | Disabled Opacity % | Manual Input | Need to change everytime we need to change color schema
Color Shade Calculation | Calculation Settings/ Percentage |  | 8% | 15% | 85% | 30% | 50%
Primary Color | Main brand/action color | #E31837 | #D11633 | #C1142F | #FBDCE1 | #EB5D73 | #E3183780
Secondary Color | Secondary buttons, supporting elements | #0A0838 | #090734 | #090730 | #DADAE1 | #545274 | #0A083880
Accent Color | Highlights, selected states, badges | #F8B4A3 | #E4A696 | #D3998B | #FEF4F1 | #FACBBF | #F8B4A380
Page Background | Overall page background | #FFFFFF | #EBEBEB | #D9D9D9 | #FFFFFF | #FFFFFF | #FFFFFF80
Surface / Card Background | Cards, panels, modals | #F6F2EA | #E2DFD7 | #D1CEC7 | #FEFDFC | #F9F6F0 | #F6F2EA80
Primary Text | Headings and normal text | #29251D | #26221B | #231F19 | #DFDEDD | #696661 | #29251D80
Secondary Text | Labels, descriptions, muted text | #4D4D4F | #474749 | #414143 | #E4E4E5 | #828284 | #4D4D4F80
Border / Divider | Borders, separators, input outlines | #E5DFD3 | #D3CDC2 | #C3BEB3 | #FBFAF8 | #EDE9E0 | #E5DFD380
Success | Success messages/status | #2E7D32 | #2A732E | #276A2B | #E0ECE0 | #6DA470 | #2E7D3280
Warning | Warning status | #B54708 | #A74107 | #9A3C07 | #F4E3DA | #CB7E52 | #B5470880
Error / Danger | Error/delete/critical status | #B42318 | #A62016 | #991E14 | #F4DEDC | #CB655D | #B4231880
Info | Information/status messages | #0A0838 | #090734 | #090730 | #DADAE1 | #545274 | #0A083880
Status | Purpose / When to Use | Font Color | Fill Color | Border Color
General | Default or neutral status where no specific workflow condition applies. Can also be used for informational or uncategorized items. | #000000 | #FFFFFF | #000000
Closed | The activity, task, issue, or request has been completed, resolved, cancelled, or otherwise requires no further action. | #2E5F13 | #D1EED0 | #2E5F13
Ongoing / In Progress | Work has started and is currently being actively progressed. The item is proceeding normally and is not presently blocked. | #8D5C1A | #F8EDA4 | #8D5C1A
Open | The item is active and requires action, but work has either not yet started or has not been formally moved into an in-progress state. | #3A59A4 | #E1EAF6 | #3A59A4
On-hold | Work has been temporarily paused due to a dependency, approval, resource constraint, customer input, or another known reason. Work is expected to resume later. | #A5A940 | #FDFFD0 | #A5A940
Attention | The item requires review, intervention, follow-up, or heightened monitoring. It may still be on schedule but has a concern, risk, dependency, or action requiring attention. | #C47135 | #F5E5D7 | #C47135
Delayed | The item has missed, or is expected to miss, its planned milestone, target date, SLA, or committed delivery timeline and requires corrective action. | #872213 | #F2CACE | #872213

## 9. Projects
Portfolio Summary |  |  |  | Qualys Patch Management - Project Status
Type | Metric | Value | Month | Project Summary | [5 empty] | Named Task List |  |  | Source Note
Projects | No. Of Projects | 23 | 2026-07-01 | Reporting_Month | Completion_Pct | Completed_Task_Count | Ongoing_Task_Count | Plan_Start_Date | Plan_End_Date | Status | Task | Task_List_Position | Note
Projects | Closed Jul’26 | 1 | 2026-07-01 | 2026-08 | 24 | 7 | 22 | 2026-07-13 | 2026-10-09 | Completed | QGS topology and tagging planning | 1 | 22 tasks in flight across QGS, endpoints and servers; slide lists 13 named ongoing task lines.
Projects | Work in Progress | 22 | 2026-07-01 | [6 empty] | Completed | Initial PM high-level design | 2
Projects | Effort in Man days | 70 | 2026-07-01 | [6 empty] | Completed | Demand meeting | 3
Demands | No. Of Demands | 30 | 2026-07-01 | [6 empty] | Completed | PM tagging workshop | 4
Demands | Closed in Jul’26 | 1 | 2026-07-01 | [6 empty] | Completed | Agent configuration profile - “PM setting” | 5
Demands | Work in Progress | 4 | 2026-07-01 | [6 empty] | Completed | License settings | 6
Demands | Effort in Man days | 13 | 2026-07-01 | [6 empty] | Completed | Server health check script | 7
[10 empty] | Ongoing | QGS deployment and configuration | 1
Top Projects & Demands Summary | [9 empty] | Ongoing | PM QGS and subnet mapping | 2
Project_Name | Status | Effort_Man_Days | Estimated_Completion_Date | [6 empty] | Ongoing | EDR and network whitelisting | 3
Meydan Network Refresh | Implementation is in progress | 8 | 2026-09-30 | [6 empty] | Ongoing | QGS-based Windows endpoints - 3rd party jobs | 4
Meydan Voice Refresh | Implementation is in progress | 12 | 2026-08-31 | [6 empty] | Ongoing | QGS-based Windows UAT endpoints - OS jobs | 5
Qualys PM and ETM | Implementation is in progress | 12 | 2026-10-30 | [6 empty] | Ongoing | QGS-based Windows prod endpoints - OS jobs | 6
DPR Firewall & Distribution Switches upgrade | Completed | 4 | [7 empty] | Ongoing | No-QGS Windows endpoints - 3rd party jobs | 7
[10 empty] | Ongoing | Windows servers UAT - OS jobs | 8
[10 empty] | Ongoing | Windows servers prod - OS jobs | 9
[10 empty] | Ongoing | Windows servers - 3rd party jobs | 10
[10 empty] | Ongoing | Linux servers - jobs | 11
[10 empty] | Ongoing | Servers’ CAR library scripts | 12
[10 empty] | Ongoing | Endpoints’ CAR library scripts | 13

## 11.Cost Optimization
Automation - License Savings | [10 empty] | CSI (Service Improvement) | [5 empty] | Reported Apr-Jul Category Totals |  |  | Reported Total (USD Annual Savings)
Month | Category | Saving_Type | License_Type | Licenses_Released | Unit_Cost_USD_Per_Month | Reported_Monthly_Saving_USD | Reported_Annual_Saving_USD | Calculated_Monthly_Saving_USD | Calculated_Annual_Saving_USD | Annual_Variance_USD | Month | Category | Initiative | Annual_Saving_USD | Description | Remarks | Category | Total_Apr_Jul_USD | Remarks | Month | Total_Annual_Savings_USD
2026-04-01 | Automation | License Cost Saved - E5..etc | SPE-F1 | 40 | 10 | 400 | 4800 | 400 | 4800 | 0 | 2026-04-01 | CSI (Service Improvement) | SIP - DDA SharePoint Site Storage Optimization, Automation | 31200 | Benefits - 1. Operational Efficiency: Streamlined DDA site storage and version management, reducing manual cleanup efforts. Site collection size optimized from 22 TB to 9 TB 2. Compliance Boosting: Reduced site risk level, with new data growth same site can be used for long period of time 3. Accuracy: Ensured precise identification and removal of redundant version files, with zero data loss 4. Cost saving: Reclaimed ~13 TB of storage, cost saving of $31200 per year | SIP was presented in April'26 monthly deck and cost saving mentioned in slide. Domain - SharePoint | Automation | 454428 | License Details/count presented in monthly deck. Unit cost taken from internet market | 2026-04-01 | 103680
2026-04-01 | Automation | License Cost Saved - E5..etc | SPE-E5 | 94 | 60 | 5640 | 67680 | 5640 | 67680 | 0 | 2026-05-01 | CSI (Service Improvement) | No SIP having cost saving | 0 |  |  | CSI (Service Improvement) | 31200 | Any savings approved & Acknowledged by DH | 2026-05-01 | 21000
2026-05-01 | Automation | License Cost Saved - E5..etc | SPE-F1 | 49 | 10 | 490 | 5880 | 490 | 5880 | 0 | 2026-06-01 | CSI (Service Improvement) | No SIP having cost saving | 0 | [5 empty] | 2026-06-01 | 103200
2026-05-01 | Automation | License Cost Saved - E5..etc | SPE-E5 | 21 | 60 | 1260 | 15120 | 1260 | 15120 | 0 | 2026-07-01 | CSI (Service Improvement) | No SIP having cost saving | 0 | [5 empty] | 2026-07-01 | 257748
2026-06-01 | Automation | License Cost Saved - E5..etc | SPE-F1 | 38 | 10 | 380 | 4560 | 380 | 4560 | 0 | [9 empty] | Apr-Jul Total | 485628
2026-06-01 | Automation | License Cost Saved - E5..etc | SPE-E5 | 71 | 60 | 4260 | 51120 | 4260 | 51120 | 0
2026-06-01 | Automation | License Cost Saved - E5..etc | MICROSOFT_365_E7 | 40 | 99 | 3960 | 47520 | 3960 | 47520 | 0
2026-07-01 | Automation | License Cost Saved - E5..etc | SPE-F1 | 533 | 10 | 5330 | 63960 | 5330 | 63960 | 0
2026-07-01 | Automation | License Cost Saved - E5..etc | SPE-E5 | 20 | 60 | 1200 | 14400 | 1200 | 14400 | 0
2026-07-01 | Automation | License Cost Saved - E5..etc | MICROSOFT_365_E7 | 151 | 99 | 14949 | 179388 | 14949 | 179388 | 0